## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a data engineer, I want to collect Azure compute and storage usage data across regions so that historical demand patterns can be analyzed for forecasting. | MUST HAVE | Azure usage dataset availability | Backend Team | 3- Completed
Sprint 1 | Sprint 1 | US002 | As a data analyst, I want to explore and analyze the collected datasets to identify trends and anomalies so that useful insights can support feature engineering. | MUST HAVE | Raw datasets | Backend Team | 3- Completed
Sprint 2 | Sprint 2 | US003 | As a data engineer, I want to clean and preprocess the collected datasets by handling missing values and standardizing formats so that the data becomes consistent for analysis. | MUST HAVE | Raw datasets | Backend Team | 3- Completed
Sprint 2 | Sprint 2 | US004 | As a data scientist, I want to perform feature engineering such as lag variables, seasonality indicators, and usage spikes so that the dataset can capture demand patterns effectively. | MUST HAVE | Cleaned dataset | Backend Team | 3- Completed
Sprint 2 | Sprint 2 | US005 | As a data scientist, I want to transform and structure the dataset into a model ready format with consistent time granularity so that machine learning models can be trained efficiently. | MUST HAVE | Feature engineered dataset | Backend Team | 3- Completed
Sprint 3 | Sprint 3 | US006 | As an ML engineer, I want to train forecasting models such as ARIMA and XGBoost using historical usage data so that future Azure service demand can be predicted accurately. | MUST HAVE | Processed dataset | Backend Team | 3- Completed
Sprint 3 | Sprint 3 | US007 | As an ML engineer, I want to evaluate the trained models using metrics like MAE and RMSE so that the most accurate model can be selected for deployment. | MUST HAVE | Trained models | Backend Team | 3- Completed
Sprint 3 | Sprint 3 | US008 | As an ML engineer, I want to perform hyperparameter tuning for models like XGBoost so that forecasting accuracy can be improved. | SHOULD HAVE | Initial trained model | Backend Team | 3- Completed
Sprint 4 | Sprint 4 | US009 | As a DevOps engineer, I want to deploy the trained forecasting model into a production environment so that real time demand predictions can be generated. | MUST HAVE | Final trained model | Backend Team | 3- Completed
Sprint 4 | Sprint 4 | US010 | As a backend developer, I want to create APIs that deliver demand forecast results to the frontend dashboard so that predictions can be visualized in real time. | MUST HAVE | Trained model | Backend Team | 3- Completed
Sprint 4 | Sprint 4 | US011 | As a frontend developer, I want to create a dashboard that displays demand forecasts and capacity insights so that stakeholders can easily visualize predictions. | COULD HAVE | Backend APIs ready | Frontend Team | 3- Completed
Sprint 4 | Sprint 4 | US012 | As a frontend developer, I want to display forecast comparison graphs (actual vs predicted demand) so that users can easily understand model performance. | COULD HAVE | Backend API integration | Frontend Team | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US001 | T1 | Collect Azure compute and storage usage dataset from multiple regions | 2026-02-02 | 2026-02-04 | Backend | Build | 3- Completed | 6 | bar: Day 1 to Day 3
US001 | T2 | Verify dataset structure and validate time series format | 2026-02-05 | 2026-02-07 | Backend | Unit Test | 3- Completed | 5 | bar: Day 4 to Day 6
US002 | T3 | Perform exploratory data analysis to identify usage patterns | 2026-02-08 | 2026-02-11 | Backend | Design | 3- Completed | 8 | bar: Day 7 to Day 10
US002 | T4 | Detect anomalies and demand spikes in the dataset | 2026-02-12 | 2026-02-15 | Backend | Unit Test | 3- Completed | 6 | bar: Day 11 to Day 14
SPRINT 2 BACKLOG
US003 | T5 | Handle missing values and clean inconsistent records | 2026-02-17 | 2026-02-18 | Backend | Coding | 3- Completed | 6 | bar: Day 1 to Day 2
US003 | T6 | Standardize data formats and timestamps across dataset | 2026-02-19 | 2026-02-21 | Backend | Coding | 3- Completed | 6 | bar: Day 3 to Day 5
US004 | T7 | Create lag variables for historical demand forecasting | 2026-02-22 | 2026-02-23 | Backend | Coding | 3- Completed | 6 | bar: Day 6 to Day 7
US004 | T8 | Create seasonality indicators and usage spike features | 2026-02-24 | 2026-02-25 | Backend | Coding | 3- Completed | 5 | bar: Day 8 to Day 9
US005 | T9 | Transform dataset into model ready structure with proper schema | 2026-02-26 | 2026-02-27 | Backend | Build | 3- Completed | 5 | bar: Day 10 to Day 11
US005 | T10 | Prepare final dataset with consistent time granularity | 2026-02-28 | 2026-03-02 | Backend | Build | 3- Completed | 5 | bar: Day 12 to Day 14
SPRINT 3 BACKLOG
US006 | T11 | Split dataset into training and testing sets | 2026-03-03 | 2026-03-04 | Backend | Coding | 3- Completed | 4 | bar: Day 1 to Day 2
US006 | T12 | Train ARIMA forecasting model using historical demand data | 2026-03-05 | 2026-03-07 | Backend | Coding | 3- Completed | 8 | bar: Day 3 to Day 5
US007 | T13 | Evaluate model performance using MAE and RMSE metrics | 2026-03-08 | 2026-03-10 | Backend | Unit Test | 3- Completed | 8 | bar: Day 6 to Day 8
US008 | T14 | Perform hyperparameter tuning for XGBoost model | 2026-03-11 | 2026-03-13 | Backend | Coding | 3- Completed | 8 | bar: Day 9 to Day 11
US008 | T15 | Train XGBoost regression model for demand prediction | 2026-03-14 | 2026-03-16 | Backend | Coding | 3- Completed | 8 | bar: Day 12 to Day 14
SPRINT 4 BACKLOG
US009 | T16 | Deploy trained forecasting model in testing environment | 2026-03-17 | 2026-03-18 | Backend | Integration Test | 3- Completed | 3 | bar: Day 1 to Day 2
US010 | T17 | Develop backend API to deliver demand forecast results | 2026-03-19 | 2026-03-21 | Backend | Coding | 3- Completed | 3 | bar: Day 3 to Day 5
US011 | T18 | Design frontend dashboard layout for demand visualization | 2026-03-22 | 2026-03-23 | Frontend | Design | 3- Completed | 4 | bar: Day 6 to Day 7
US011 | T19 | Integrate dashboard with backend APIs for real time forecasts | 2026-03-24 | 2026-03-26 | Frontend | Integration Test | 3- Completed | 4 | bar: Day 8 to Day 10
US012 | T20 | Create forecast comparison graphs (actual vs predicted demand) | 2026-03-27 | 2026-03-28 | Frontend | Coding | 3- Completed | 4 | bar: Day 11 to Day 12
US012 | T21 | Finalize dashboard visuals and verify output accuracy | 2026-03-29 | 2026-03-30 | Frontend | System Test | 3- Completed | 3 | bar: Day 13 to Day 14

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Working with incomplete or undocumented datasets | Created structured dataset and generated initial EDA report
Sprint 2 | Day 2 | Manual and inconsistent data cleaning methods | Produced cleaned and feature engineered dataset ready for modeling
Sprint 3 | Day 1 | Training models without proper validation | Selected best performing forecasting model after hyperparameter tuning
Sprint 4 | Day 2 | Delaying backend–frontend integration until the end | Successfully deployed forecasting API and built interactive dashboard

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-02 | 2026-02-16 | Backend Team | Collect data across sourcess and perform initial dataset exploration | Working with incomplete or undocumented datasets | Collaborative data exploration and documentation | Created structured dataset and generated initial EDA report
2 | Sprint 2 | 2026-02-17 | 2026-03-02 | Backend Team | Implement data preprocessing pipeline and perform feature engineering such as lag features and seasonality indicators | Manual and inconsistent data cleaning methods | Automating preprocessing scripts for consistency | Produced cleaned and feature-engineered dataset ready for modeling
3 | Sprint 3 | 2026-03-03 | 2026-03-16 | Backend Team | Train forecasting models such as ARIMA and XGBoost and evaluate them using MAE and RMSE metrics | Training models without proper validation | Iterative model experimentation and performance comparison | Selected best-performing forecasting model after hyperparameter tuning
4 | Sprint 4 | 2026-03-17 | 2026-03-30 | Backend + Frontend Team | Deploy trained forecasting model, develop APIs for prediction delivery, and create dashboard for visualization of forecast results | Delaying backend–frontend integration until the end | Continuous integration and testing between backend APIs and frontend dashboard | Successfully deployed forecasting API and built interactive dashboard with forecast comparison graphs